## Sprint 1
User Story | TO DO | In Progress | Impediment | To Verify | Done
1. Customer Login, Admin Login, Admin Approval[Riya Hoondlani] | 1.1 Develop repositories,services,controllers for customer login 1.2 Develop the angular components for customer login 1.3 Integrate Front end and back end | 1. Admin side code for approval backend. 2. Admin side dashboard for approval |  | 1. Admin side code for approval backend. 2. Admin side dashboard for approval | 1. Customer login back end 2. Customer login front end. 3. Entity classes 4. Back end of loginTo do- 5. AdminLogin backend 6.AdminLogin front end 7. Apply checks to login and password fields at both customer and admin end
2. Create Account[Shantanu Bisht] | 2.1 Develop repositories,services,controllers for customer login 2.2 Develop the angular components for customer login 2.3 Integrate Front end and back end | 1.Back end of registration almost done where i am able to extract and save data in data base. Now inserting all the required fields.
3. Fund Transfer[Pradeep] | 3.1 Develop repositories,services,controllers for fund transfer 3.2 Develop the angular components for fund transfer 3.3 Integrate Front end and back end | Completed backend and frontend and integration few validations are pending and working on them working on fetching list of accounts and list of beneficiaries
4. Add Beneficiary, Change Password, Forget Password[Neelam Tiwari]. | Addition of Few more things in FrontEnd, Dashboard, Routing, Redirection | Addition of few more validations .Addition of Few more things in FrontEnd, Dashboard, Routing, Redirection |  |  | 4.1 Develop repositories,services,controllers for Add beneficiary,Changing Password,ForgetPassword. 4.2 Develop the angular components for Adding Add beneficiary,Changing Password,ForgetPassword. 4.3 Integrate Front end and back end of respective functionalities.

## Sprint 2
User Story | TO DO | In Progress | Impediment | To Verify | Done